## Sheet1
Sprint Start Date | 2019-10-29 | Day of the Sprint | Target | Actual
Sprint End Date | 2019-11-05 | 0 | 15 | 15
Sprint Length (Days) | 7 | 1 | 12.8571 | 12
Sprint Points | 15 | 2 | 10.7143 | 9
Expected Average Daily Sprint Points | 2.1429 | 3 | 8.5714 | 6
|  | 4 | 6.4286 | 3
Completion Time | 5 | 5 | 4.2857 | 0
Average Daily Sprint Points Completed | 3 | 6 | 2.1429 | 0
|  | 7 | 0 | 0