## Sprint backlog
Product backlog ID | Item | Task |  | Total Time
|  | In Developement | Status
Scrum
| Product Backlogs | Caitlin & Savannah |  | 1 | Completed
| Sprint Planning | Caitlin & Savannah |  | 1 | In progress
| Sprint backlogs | Caitlin |  | 1 | No progress
| Presentation | Sav |  | 2
Program
3 | Create Gui | Luke / Hayden / Jackson / Darius |  | 3
2 | Build API for new headlines | Hayden and Luke |  | 2
5 | Authorize Spotify and Query Results | Luke & Hayden |  | 1
6 | Make a word extractor to extract words from headlines | Luke & Hayden |  | 1
4 | Make the playlist show up | Luke & Hayden |  | 1
Testing
3 | Test GUI | Luke & Hayden |  | 1
2 | Test uptodate News playlist | Luke & Hayden |  | 1
7 | Class Diagram | Darius |  | 1
8 | Pair Programming Log: Driver Darius Observer: Jackson | Darius |  | 1
9 | Pair Programming Log: Driver Jackson Observer: Jackson | Jackson |  | 1
10 | Description of tasks per week | Darius |  | 1
11 | Sprint Chart Generator | Hayden |  | 1